PROJECT PLANNING PHASE

Product Backlog, Sprint Planning, Stories & Story Points

| Date | March 2026 |
| --- | --- |
| Team ID | 699d5f8ac40b5ad0e9ee598f |
| Project Name | PlantCare AI |
| Maximum Marks | 8 Marks |

# Product Backlog & Sprint Schedule (4 Marks)

| Sprint | Functional Req (Epic) | User Story No. | User Story / Task | Story Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Setup | USN-1 | As a developer, I can set up the Flask project structure with required folders (static, templates, model, utils, docs, notebooks). | 2 | High |
| Sprint-1 | Project Setup | USN-2 | As a developer, I can configure the Python virtual environment and install all required dependencies from requirements.txt. | 1 | High |
| Sprint-1 | Project Setup | USN-3 | As a developer, I can create config.py to store global configuration variables (model path, upload folder, allowed extensions). | 1 | High |
| Sprint-1 | Model Training | USN-4 | As a data scientist, I can load and explore the Plant Disease dataset in a Jupyter notebook. | 2 | High |
| Sprint-1 | Model Training | USN-5 | As a data scientist, I can preprocess the dataset (resize to 224x224, normalize, split train/val/test). | 3 | High |
| Sprint-2 | Model Training | USN-6 | As a data scientist, I can build the MobileNetV2 transfer learning model using TensorFlow/Keras. | 3 | High |
| Sprint-2 | Model Training | USN-7 | As a data scientist, I can train the model and achieve satisfactory validation accuracy on 38 disease classes. | 5 | High |
| Sprint-2 | Model Training | USN-8 | As a data scientist, I can evaluate the model (accuracy, precision, recall, F1-score) and save as plant_disease_model.h5. | 3 | High |
| Sprint-2 | Backend | USN-9 | As a developer, I can create utils/preprocessing.py to load and preprocess an image for model inference. | 2 | Medium |
| Sprint-3 | Backend | USN-10 | As a developer, I can create app.py with Flask routes: GET /, GET /upload, POST /predict, GET /about. | 3 | High |
| Sprint-3 | Backend | USN-11 | As a developer, I can implement the /predict route to accept image upload, preprocess it, and return model prediction. | 3 | High |
| Sprint-3 | Backend | USN-12 | As a developer, I can load class_names.json and map model output index to disease name. | 1 | High |
| Sprint-3 | Frontend | USN-13 | As a user, I can view the home page with app introduction and navigation links. | 2 | Medium |
| Sprint-3 | Frontend | USN-14 | As a user, I can navigate to the upload page and upload a plant leaf image (PNG/JPG/JPEG). | 2 | High |
| Sprint-4 | Frontend | USN-15 | As a user, I can view the prediction result page showing the detected disease name. | 2 | High |
| Sprint-4 | Frontend | USN-16 | As a user, I can view the About page explaining the application and team. | 1 | Low |
| Sprint-4 | Testing | USN-17 | As a developer, I can write and run unit tests for preprocessing and prediction functions. | 3 | High |
| Sprint-4 | Testing | USN-18 | As a tester, I can perform integration testing on all Flask routes. | 2 | High |
| Sprint-4 | Deployment | USN-19 | As a developer, I can deploy the application locally and verify all features work end-to-end. | 2 | Medium |
| Sprint-4 | Documentation | USN-20 | As a developer, I can write the complete project README with setup instructions, architecture, and usage guide. | 1 | Medium |

# Project Tracker, Velocity & Burndown Chart (4 Marks)

## Sprint Tracker

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 9 | 7 Days | 01 Mar 2026 | 07 Mar 2026 | 9 | 07 Mar 2026 |
| Sprint-2 | 13 | 7 Days | 08 Mar 2026 | 14 Mar 2026 | 13 | 14 Mar 2026 |
| Sprint-3 | 11 | 7 Days | 15 Mar 2026 | 21 Mar 2026 | 11 | 21 Mar 2026 |
| Sprint-4 | 11 | 7 Days | 22 Mar 2026 | 28 Mar 2026 | - | - |

## Velocity Calculation

Total Story Points = 44 | Total Duration = 4 Sprints x 7 Days = 28 Days

Average Velocity (AV) = Total Story Points Completed / Number of Sprints

AV = (9 + 13 + 11) / 3 = 33 / 3 = 11 story points per sprint

Average Velocity per Day = 11 / 7 = ~1.57 story points per day

## Burndown Chart Data

| Day | Sprint | Story Points Remaining |
| --- | --- | --- |
| Day 1 | Sprint-1 | 44 |
| Day 7 | Sprint-1 | 35 |
| Day 8 | Sprint-2 | 35 |
| Day 14 | Sprint-2 | 22 |
| Day 15 | Sprint-3 | 22 |
| Day 21 | Sprint-3 | 11 |
| Day 22 | Sprint-4 | 11 |
| Day 28 (Target) | Sprint-4 | 0 |

Note: A Burndown Chart graphically represents work remaining over time. The ideal line drops linearly from 44 (Day 1) to 0 (Day 28). The actual line tracks real sprint completions. Any deviation above the ideal line indicates sprint delay; below indicates ahead-of-schedule delivery.